## STP
SI.no | issue | screen | Status | est. in hrs | remarks | Type
1 | Initial Record for START cannot be setup for Sub Process Action SCR, as "Continue process" cannot be setup to mention the process. | sub process |  | 18 | we need to design in different way( on discussion call we can remove proces master and fill all sub process and just assignment flow can be setup like in dsg final setup) | Fixes
2 | calling sub process inside sub process. it may go infinite loop check. | sub process |  | 2 | test | Fixes
3 | Sub Process Action shows API in listing Screen. But on edit, shows SCR in detail popup | sub process | Completed | 1 | screen change | Fixes
4 | If the "Action From" is "Continue Process" for Success what does the program do as there is no ID like API/Screen. | sub process |  | 3 | test | Fixes
5 | on sub process after choosed the screen as action its not remiving the query builder | sub process |  | 1 | test | Fixes
7 | data in dattable of sub process "sub process action column value is in correct" | sub process | Completed | 1 |  | Fixes
8 | STP Starting taking so much time, need to check quries. |  | Completed | 3 | test | Fixes
9 | multiple api's in single swagger is not allowed(need to check and if possible enable multiple api's) | api master |  | 2 |  | Fixes
10 | header is not able to change into AHD(enable auth name response fields to map like HD) | api master |  | 3 |  | Fixes
12 | need to handle the STP_FIELDS_MASTER update submit approval on apporved record it creating a V record and A record, but not able to see in authorize screen. Because the main api master record is not marked as V. | api master |  | 1 |  | Fixes
14 | If the application is sent for approval or Deviation, the approving authority should approve and application and should not be sent to the screen where it was invoked. Setup in STP to be checked when Calling Screen and destination screen are different. Need to discuss on maintaining application stage | sub process | Completed | 0 | have taken into account on los_al | Fixes
15 | why reponse fields setup is not needed ? | api master |  | 3 |  | Fixes
16 | bean refresh not working |  | Completed | 2 |  | Fixes
17 | api master update deleting records in STP_FIELDS_MASTER. on Authorize. |  |  | 2 |  | Fixes
18 | update of stp fields master data is not comming for status V. |  |  | 2 |  | Fixes
19 | process master Authorize |  | Completed | 2 |  | Fixes
20 | Need to maintain stp request id against application id or email or phone something in stp, need to fetch process of application in stp by some sort of way to fix - (find the process) |  |  | 3 | need to discuss on can store the application id in stp, not all idnumber full names. | Fixes
21 | request process screen in stp is not working, shows wrong entry - list process status screen |  |  | 3 |  | Fixes
22 | const element decrypt and encrypt data is not working(test case is when user entered string is having two + its not decrypted properly) |  |  | 4 | might can the encrypt and decrypt logic. If that’s the solution, we need to update all old records in automated way | Fixes
23 | screen fields and caller inputs has to be come from DSG catalog table |  |  | 9 | screen change and flow test | Fixes
24 | swagger testing with different swaggers and review code |  |  | 18 | need to spend 1 day to review and look for bottlenecks and start development | Fixes
27 | how to set Message field of API response when the condition is failed on query builder ( by getting message we can populate in DSG to hanndle) |  |  | 4 |  | enhancement
28 | priority for parallel processing in sub process, need to check how its working and screen | sub process |  | 4 |  | Fixes
29 | mapping API response fields to another API currenlty for elements , need to check for Array and objects as well if possible | API master |  | 4 |  | enhancement
30 | Callback API's (async and sync) |  |  | 8 |  | enhancement
31 | We need to identify how to automatically write a memo and what text to add. can it also be done at STP level?(same as update stage) | sub process | Completed | 8 |  | enhancement
32 | Create a common routinue of save Application details in api master with "Save on screen" type of API. and call automatically if the process is comes from the screen. ex: LOS_AL. |  |  | 8 |  | enhancement
33 | Need to move query builder to popup for both the actions | sub process |  | 16 |  | enhancement
34 | Is comparable on retrigger column in STP fields master and write a logic to remove the request fields which are all marked as Y in request comparison |  | Completed | 8 |  | enhancement
35 | Multiple query creation in sub process like multiple if condition and default else condition(refer the below mentioned SS). Move tick mark action from and related fields into jquery builder | sub process |  | 16 |  | enhancement
36 | add meesage field as part of query builder on true actions along with action from field. Get static or API for message field. If static text field and for API get from api response. | sub process |  | 8 |  | enhancement
37 | Need to add "Move to approval" in STP action from, and check formId from rule API and if values Exist get Screen Id, Approval Screen Id, Nxt Process Id. | sub process |  | 8 |  | enhancement
38 | for approvalId jquery query builder , not able to check for null. Need to fix that. | sub process |  | 16 |  | enhancement
39 | shouldAPI fucntion is not working properly | stp process |  | 5 |  | Fixes
40 | add auto generated id as source from option | stp fields master |  | 4 |  | enhancement

## LOS-AL
Si.no | task | Project | remarks | Priority | Est. in hrs | assigned to | status | Date of completion
13 | need to update the application whenever api getting success or failure | STP | Along with scr and API changes | 1 | 8 | barath | Completed | 2025-03-24
10 | Add and manage guarantors, co-applicant screen | DSG |  | 2 | 8 | Bala | Completed | 2025-03-24
| Rule setup(Need to create rule for co-application based on parameters) | RULE | Need to be identified the fieds to create rule | 2 | 3 | Bala | Completed | 2025-03-25
12 | Manage Approvals Scr | DSG |  | 3 | 3 | barath | Completed | 2025-03-25
| Multiple approval API handling(internal API) | API |  | 3 | 8 | barath | Completed | 2025-03-26
| stp setup | STP | The same process can be reused from primary applicant | 4 | 2 | barath | Completed | 2025-03-26
| Rule setup(Need to create rule for co-application based on parameters) | STP | Same process is called so no additional Rules created | 4 | 5 | barath | Completed | 2025-03-27
11 | Manage Application Scr | DSG | Working on can be added more than one co-application to the application | 4 | 3 | Bala | Completed | 2025-03-25
| Need to be handled modify and restart in manage application | API |  | 4 | 4 | Bala | Completed | 2025-03-26
| rules (interest rate with margin and Credit decission Rule) | STP | Once fields identified and policy created will add in STP | 5 | 1 | barath | Completed | 2025-03-27
4 | repayment schedule(with margin) | DSG | need to do changes If required | 5 | 4 | barath | Completed | 2025-03-28
| common api repayment | API | Api added, need to test with flow | 5 | 4 | barath | Completed | 2025-03-28
14 | Iframe feauture | DSG |  | 6 | 6 | Bala | Completed | 2025-03-27
| Template creation for document upload | DSG |  | 6 | 16 | Bala | Inprogress | 2025-04-02
| need to remove commo (if the field is amount field) while creating request for api | DSG |  | 6 | 0.5 | Bala | Completed | 2025-03-27
7 | documents upload screen | DSG |  | 7 | 6 | bala | Completed | 2025-04-03
| upload and save in child doc internal api | STP and API |  | 7 | 6 | barath | Completed | 2025-04-01
8 | Proposal for disbursement screen | DSG |  | 8 | 8 | barath | Completed | 2025-04-02
| stp setup | STP |  | 8 | 2 | barath | Completed | 2025-04-03
| customer creation and all tables insertion (like handover) (inprogress) | STP and API | Need to check paywallet and GL api for loan booking and customer creation | 8 | 4 | barath | Completed | 2025-04-03
9 | loan approval screen | DSG |  | 9 | 6 | bala | Completed | 2025-04-04
| mutiple approval queue | API |  | 9 | 4 | bala | Completed | 2025-04-04
| All table record need to be changed | STP |  | 9 | 2 | barath |  | 2025-04-03
| Need to add "Move to approval" in STP action from, and check formId from rule API and if values Exist get Screen Id, Approval Screen Id, Nxt Process Id. | STP |  | 10 | 8 | barath | Completed | 2025-04-04
| add formId, message Field in part of Rule response and create a rule to send the loan approval form to test in AL in approval for disbursement stage | RE |  | 10 | 8 | bala | Completed | 2025-04-07
3 | Loan details screen | DSG |  |  | 8 | barath | Completed
| get vehicle details (common api or lms api) | STP |  |  | 4 | barath | Completed
| save data (internal api) | STP |  |  | 4 | barath | Completed
| cibil api | CAS and STP |  |  | 2 | barath | Completed
| save cibil data | STP |  |  | 1 | barath | Completed
| uan validation and get data based on uan (common api) | CAS and STP | Uan from Aadhar sample API in CAS |  | 3 | barath | Completed
| Employment History By uan from CAS | CAS and STP |  |  | 4 | barath | Completed
| Employment data storing (internal api) | STP |  |  | 1 | barath | Completed
| calculate ratios | API and STP |  |  | 4 | barath | Completed
| rules (interest rate with margin and Credit decission Rule) | RE |  |  | 1 | bala | Completed
| get existing loan details api(internal lms and cibil) | API and STP | API's written , need to add in STP Process if we need |  | 1 | barath | Completed
Common save API for save all external api response in LOS
Prior task from other project module to complete AL(Yellow background)
1

## RULE_ENGINE
S.No | Project | Screen | Remarks and Changes | Added Remarks | Status | Date of completion
1 | Rule Engine | Rule Field | Rule type check box should create dynamicaly based on rule type dropdown |  | Completed | 2025-01-29
2 | Rule Engine | Rule Field | Based on list screen rule type, add screen also should click check box |  | Completed | 2025-01-29
3 | Rule Engine | Rule Field | Need to standardize string or text in datatype in user defined and defined fields |  | Completed | 2025-01-29
4 | Rule Engine | Rule Field | Need to check field description is mandatory or not ??? |  | Completed | 2025-01-29
5 | Rule Engine | Rule Field | Table name coming as description but fields coming as column name need to check |  | Completed | 2025-01-29
6 | Rule Engine | Rule Field | For the workflow rule type , only required tables should come in table dropdown |  | Completed | 2025-01-29
7 | Rule Engine | Rule Creation | Should maintain rule name can convert camelCase (java naming convention)onblur or need to be maintained in system and also should allow some fixed valid characters |  | Completed | 2025-02-04
8 | Rule Engine | Rule Creation | Need to check weightage is mandatory or need to be removed | to be hidden | Completed | 2025-02-04
9 | Rule Engine | Rule Creation | Amounts and numbers field should format in jquery builder fields based on selected fields |  | Completed | 2025-02-04
10 | Rule Engine | Rule Creation | font is too big in rule text area and fields should show description not column name |  | Completed
11 | Rule Engine | Rule Field / Rule Creation | Need to check response field creation and usage | For the request field can create user defined and table fields like that we need to create response field as well. For now we can create user defined response field only. | Completed
12 | Rule Engine | Rule Creation | Add popup X close button |  | Completed
13 | Rule Engine | Rule Creation | Field id usage need to check in code |  | Completed | 2025-02-04
14 | Rule Engine | Rule Creation | if i delete the last one, the prev condition also gets the and/or removed - Ravi T (Jquery Builder) |  | Completed
15 | Rule Engine | Rule Creation | reduce the height of each row including the and/or row and also reduce all the padding around each of the rows as lot of space is being wasted (Jquery Builder) |  | Completed
16 | Rule Engine | Rule Creation | On click of reset - issue |  | Completed
17 | Rule Engine | Rule Creation | Response fields are not coming, for the new rule type - need to check |  | Completed | 2025-02-04
18 | Rule Engine |  | Drool file conversion to map and need to be changed rule invoke API accordingly |  | Completed
19 | Rule Engine |  | Group view hanging.. Need to check |  | Completed
20 | Rule Engine |  | Field to field mapping |  | Completed
21 | Rule Engine |  | Calculation in request as well as response |  | Completed
23 | Rule Engine |  | Rule file crud should be done from src resource folder not from drive
24 | Rule Engine |  | Need to check the group is exist or not before invoke rule(Request validation) |  | Completed
25 | Rule Engine |  | Able to access field as well as text labels |  | Completed
26 | Rule Engine |  | Mapping table and field for user defined fields need to ask in screen and dynamic record fetch from db |  | Completed
27 | Rule Engine |  | Field name trim need to check |  | Completed
28 | Rule Engine |  | formula label need to be change as compute |  | Completed
29 |  |  | Need a discussion about response of rule |  | Completed
30 | Rule Engine |  | common response field addition part of Api response, and handling mapping. And add drop down or text field to enter the loan form id if any approvals needed? |  | Completed

## DSG
S.no | Fixes and enhancement | screen | Status | Est. in hrs | Remarks
1 | the:src need to add in dsg. | html creation | completed
2 | add request from response of previous api. | service calls | completed
3 | add request value is not able to enter empty string | service calls | completed
4 | adding dependcies script tag and cutsom script tag into html. | html creation | completed
5 | after js created and removing a element form hmtl. its not removing from js. | final generation | completed
6 | request popup not working | service calls | completed
7 | labels on inputs background spaces are very big | html creation | completed
8 | file name not generated correctly | html creation | Completed
9 | fragment and insert tag is not synced | html creation | Completed
10 | th:value in inputs and hidden ( ${description} ) | html creation | Completed
11 | data. Request entry is not populating ? So its failing on data retrieve | service calls | completed
12 | case sensitive issues (FILES) | Generation | completed |  | #8 duplicate
13 | OTP Template | html creation | completed
14 | When base folder is not available it should throw out with invalid folder name | Generation | Completed
15 | style=" col-md-4" instead of class=" col-md-4" | html creation | completed
16 | Common script and links should be in created html defaultly | Generation | completed |  | #4 duplicate
17 | passing some id as 1737719251873ceS4 which is not available in db. | ? | Completed |  | Need to understand the issues
18 | If forms are used in screen, default form validation condition has to be created in db | html creation | Completed |  | eg : if (validateForm('RuleFieldForm')) Each panel has one form. So, if we have multiple panel in single screen, then how to use validateForm - need to check single form validation completed
19 | Final setup shrink issue | Final Setup | Completed
20 | Common STP Invoke - static code in js | Service Calls |  |  | Need to be discussed
21 | Object inside object in request | Service calls | Completed
22 | Panel arrow issue |  | Completed
23 | Field values alignment - based on (number or text) (amount format) |  | Completed
24 | Date field min and max need to be done dynamically |  | Completed
25 | DB has to be moved from mysql to mssql | DB
26 | More than 1 html element with same name restriction handling |  | Completed
27 | Element cut and paste from one panel to another panel handling |  | Completed
28 | Code + description in option tag |  | Completed
29 | Form validation need to be done - and should panel open if field is empty |  | Completed
30 | sidebar on hover the sub menus labels are not visible |  | Completed
31 | Custom attr adding and fetching |  | Completed
32 | While doing form validation span tags (this field is mandatory) showing into the field. It should show under the field |  | Completed
33 | toastr message can be throw from api response |  | completed
34 | If field is empty, need to sort out that, put it as N/A or empty like that need to change - cause of white bg for label |  | Completed |  | We have an option called Value, through that we can setup direct value
35 | View and delete screen need to check |  | completed
36 | need to remove commo (if the field is amount field) while creating request for api | BE | completed | 0.5
37 | TH option popup doesn't destroy, need to fix - need to fix this -in all popup |  | Completed
38 | Droppable form dropdown need to check |  | completed
39 | Internalization and html files are creating two different path need to check | BE |  | 0.5
40 | render: function(data, type, row) { return data ? data : "N/A"; // Display "N/A" if field is missing } and alignment of row in data grid |  | completed
41 | Final setup reorder - done by sortable |  | completed
42 | Computation for assigning to fields and for condition |  | completed
43 | Computed fields as api request |  | completed
44 | Function calling |  | completed
45 | script and link file |  | Completed
46 | Need to think about saving event handles for all the fields in BE, currently in screen | BE |  | 4
47 | Whole queries need to write efficiently | BE |  | 4
48 | Make rows as copy or cut and paste in final setup instead of sortable | Final Setup |  | 4
49 | Screen delete should not remove from db - status has to be changed | BE |  | 2
50 | API Request creation popup design need to be changed | API Request |  | 1
51 | Need to maintain data grid load and their button events need to maintain differenty | Validation and Prop |  | 0.5
52 | Need to filter type of fields based on service type | Validation and Prop |  | 0.5
53 | Copy function - this function copies the same screens along with other artifacts for reuse in other functionality. Ex: Listing screen can be reused in GL and PL | FE and BE |  | 8
54 | Template - Creation of Template of the screen so that I can reuse any where |  |  |  | Need to be discussed
55 | Need to implement like this screen is not support to navigate to other screens |  | Completed
56 | Iframe feauture |  | completed | 6 | Completed
57 | While creation of project we need to create packages, pom, properties, security
58 | Template creation for document upload | FE and BE | completed | 16
59 | can we have option to set default values if .val is null undefined |  |  | 4
60 | data table fetaures has to be added. Based on AL requirement(Button hidden show)
61 | need to give option load image / pdf from byte code
62 | sybmols on fields as prefix or suffix on values (cuurency symbol)
63 | Parsefloat for decimal field values (computation, condition and value change etc)
64 | datatable data column can be no wrap option
65 | Datatable can be hide and show
66 | should take a min and max value also for numeric fields including amounts,percentages etc. Based on that jQuery script should get generated
67 | default date can be taken from db
68 | Amount alignment
69 | disabling copy and paste in inputs tags

## CAS
Si.no | task | Status | Est. in hrs | Assigned to
1 | retry mechanism in the common API's will have to be implemented based on retry parameter |  | 8 | Barath

## demo comments
Demo date | 2025-04-11
S.No | Fixes | Remarks | Additional remarks | Est. in hrs | Assigned to | New status | Status | Completed date | issue reason | Worked By
1 | re-enter id number in id verification with original is hashed |  |  | 2 | bala |  | Completed | 2025-04-15 | missed | barath
2 | how many digits and what type of values can be entered also can get from DSG for id number | This enhancement was done after generating this files | Failed - due to min length check | 4 | bala | Completed | Completed | 2025-04-16 | missed | barath
3 | put label for converted age instead just 24 |  | "age" instead on "converted age" | 0.25 | bala | Completed | Completed | 2025-04-15 | default design by ravi | barath
4 | new customer has to be shown differently |  |  | 1 | barath |  | Completed | 2025-04-16 | default design by ravi | barath
5 | gaps between fields not same for all fields |  |  | 1 | barath |  | Completed | 2025-04-17 | bug in dsg | barath
6 | document view in personal info has to be checked from DSG,(aadhar view) |  |  | 4 | bala |  | Completed | 2025-04-16 | not possible in dsg | barath
7 | validate period of stay in perosnal info screen |  |  | 0.25 | barath |  | Completed | 2025-04-16 | missed | barath
8 | validate PAN (size, get rouinte check) |  |  | 0.5 | barath |  | Completed | 2025-04-16 | bug | barath
9 | system is slow on submits |  |  | 2 | barath |  | Completed | 2025-04-16 | net work issue | common
10 | pan number tick mark and cross mark |  |  | 1 | barath |  | Completed | 2025-04-21 | not possible in dsg | barath
11 | check vehicle type('New) how its populated |  |  | 2 | barath |  | Completed | 2025-04-16 | bug | barath
12 | Vehicle details all fields to checked and re load to default on any previous field changes |  |  | 2 | barath |  | Completed | 2025-04-17 | missed | barath
13 | add one or more records on dealers drop down and test |  |  | 2 | barath |  | Completed | 2025-04-21 | testing criteria | barath
14 | currency symbol |  |  | 3 | bala |  | Completed | 2025-04-21 | enhancement in dsg | common
15 | amount align and format |  |  | 3 | bala |  | Completed | 2025-04-17 | missed | bala
16 | total cost has to be disabled |  |  | 0.25 | barath |  | Completed | 2025-04-16 | missed | barath
17 | wht is to be removed and change to GST( check the effect of that field) | checked on LMS, found out this field is used on disburement queue | disussed with rvai, Check on Tax details whether WHT is taken or not? | 8 | barath |  | Completed |  | need to discuss | barath
18 | panel arrow errors(check by recreating the html) |  |  | 2 | bala |  | Completed | 2025-04-21 | missed | bala
19 | tenure has to be validated by min term and max term from param product |  |  | 3 | barath |  | Completed | 2025-04-17 | missed | barath
20 | tenure label to be in months or what | need to discuss(raised by ramanan) |  | 0.5 | barath |  | Dropped |  | enhancement | barath
21 | base rate in percentage or not label change |  |  | 0.25 | barath |  | Completed | 2025-04-17 | missed | barath
22 | manger margin validate based on margin(check with margin In GL) |  |  | 0.5 | bala |  | Completed | 2025-04-21 | missed | barath
23 | repayment schedule is to be validated | validated through online, validated with Narsing |  | 2 | barath |  | Completed | 2025-04-17 | to validate | barath
24 | date picker not working on Disbursement date(Jquery) |  |  | 2 | bala |  | Completed | 2025-04-17 | library issue | common
25 | edit of bank account number |  | After verification still its asking to reverify while doing reloading the screen on click of sumbit | 3 | bala | Completed | Completed | 2025-04-15 | missed | barath
26 | deductbales table issue(library issue) |  |  | 2.5 | bala |  | Completed | 2025-04-17 | library issue | bala
27 | payable column in deductables value is zero. Check that |  |  | 2 | bala |  | Completed | 2025-04-17 | missed | bala
28 | total deductions has toi be full right |  |  | 2 | bala |  | Completed | 2025-04-17 | missed | bala
29 | payyee name (check what effect) |  |  | 3 | bala |  | Completed | 2025-04-21 | Need to check | bala
30 | need to check loading message is not show on submit of proposal of disbursement |  |  | 2 | bala |  | Completed | 2025-04-16 | library issue | common
31 | change "move to approval" wrning into success |  |  | 0.5 | barath |  | Completed | 2025-04-15 | changes | barath
32 | pending approval counts in Manage approval list screen |  |  | 2 | barath |  | Completed | 2025-04-15 | missed | barath
33 | approval details of multiple approval in approvals screen. To know the details of who and what and when they did. |  | Approval remarks can be change, so it should be empty every approval | 8 | barath | Completed | Completed | 2025-04-16 | missed | barath
34 | check the reject of multiple approvals |  |  | 4 | barath |  | Completed | 2025-04-15 | missed | barath
35 | add customer id in loan booked screen |  |  | 1 | bala |  | Completed | 2025-04-16 | enhancement | bala
36 | check whether we can call loan booking process directly after the all approvals are done. Instead of restart in Mange application | For now muliple response handling is not enabled in STP. So managed to call from JS itself STP to continue the process. | Need to discuss along with Ravi T | 4 | barath | Completed | Completed | 2025-04-21 | missed | barath
37 | all tables records has to be checked after loan booking |  | pending to be validated along with Narsing | 8 | bala |  | Completed |  | check values | bala
38 | Need to check the link between product type and the vehicle details |  | discussed with ravi, it’s a enhancement in delaer module to add product type on showroom level and in los API. |  | barath
39 | Currency exchange is not populating properly and symbol also not changed |  | newly raised by Ramana |  | bala | Completed | Completed
standard common response save api in stp
Need to link with dealer and product type

## Testing issues
S.no | Issues | Raised date | Raised By | Status | Completed date
1 | After entering Addhar if otp is given wrongly first time than ven after giving the correct otp second time system not validating | 2025-04-22 | Narsing | Ready For Testing | 2025-04-24
2 | Manage application view Aprove Button is there | 2025-04-22 | Narsing | Ready For Testing | 2025-04-24
3 | Multiple Approvers same id allowing for all approvers. System should accept as per multiple approvers set up | 2025-04-22 | Narsing | Ready For Testing | 2025-04-24
4 | Disbursement info screen :- First due date is comming from Date_master ( 15-02-2023 ) but Disbursement date is comming from system date ( 22-04-2025 ). All thedates should be date_master | 2025-04-22 | Narsing | Ready For Testing | 2025-04-24
5 | Period of stay in Address is accepting 0 - 60 only . it should accept the more than 60 also? why restricted to 60? | 2025-04-22 | Narsing | Ready For Testing | 2025-04-24
6 | Disbursemnt approval - allwing maker id for all approvals . should be as per Form approval master | 2025-04-22 | Narsing | Ready For Testing | 2025-04-24
7 | System is slow | 2025-04-25 | Narsing
8 | Manage application if we open the application in 'View' mode is selected and This application is already submitted for approval. using the above Green menus system allowing to edit the application. We should not allow to edit the application by selecting thru 'View' option. After approval 'Document apporval' screen, here also if i go with 'View' button system is going to EDit button if you select the green tabs. For Manage pending for approval also | 2025-04-25 | Narsing | Ready For Testing | 2025-04-28
9 | For approval are we using Maker checker or Form approval master different user id's. I have created the application with id 'knprasad' and submitted for approval. Three approvals are required so I login as user id 'a-ravi.t' and completed 3 approvals using the same id. | 2025-04-25 | Narsing | Ready For Testing | 2025-04-28
10 | system should not allow Disbursement date > First due Date | 2025-04-25 | Narsing | Ready For Testing | 2025-04-29
11 | Proposal for Disbursement approval form :- system is allowing with same id for approval of submit for approval and all three approvers | 2025-04-25 | Narsing | Ready For Testing | 2025-04-28
12 | in Search screen if we enter the customer id we are getting customer details but if we give contract number not listing the customer data? | 2025-04-25 | Narsing | Ready For Testing | 2025-04-28

## Table List
S.No | Table Name
1 | APPLICATION_DETAILS
2 | REPAYMENT_SCHEDULE
3 | CUSTOMER_DETAILS
4 | ADDRESS_DETAILS
5 | DEMOGRAPHICS
6 | CHARGE_TXN_SUMMARY
7 | CHARGE_TXN_DETAILS
8 | APPICATION_FEE_CHARGES
9 | CUST_ID_DETAILS
10 | TAX_DETAILS
11 | CUSTOMER_BANK_DETAILS
12 | CREDITLINE_CREDIT_LIMIT
13 | VENDOR_PAYMENT
14 | CREDIT_LINE_DETAILS
15 | ACCOUNT_DETAILS
16 | CONTRACT_NEW
17 | APPLICATION_REPAYMENT_SCHEDULE